## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  | Period Highlight: |  | 60 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week commencing: |  |  |  | (2 periods = 1 week, 4 periods = 1 sprint)
[7 empty] | 2020-10-16 |  | 2020-10-23 |  | 2020-10-30 |  | 2020-11-06 |  | 2020-11-13 |  | 2020-11-20 |  | 2020-11-27 |  | 2020-12-04 |  | 2020-12-11 |  | 2020-12-18 |  | 2020-12-25 |  | 2021-01-01 |  | 2021-01-08 |  | 2021-01-15 |  | 2021-01-22 |  | 2021-01-29 |  | 2021-02-05 |  | 2021-02-12 |  | 2021-02-19 |  | 2021-02-26 |  | 2021-03-05 |  | 2021-03-12 |  | 2021-03-19 |  | 2021-03-26 |  | 2021-04-02 |  | 2021-04-09 |  | 2021-04-16 |  | 2021-04-23 |  | 2021-04-30 |  | 2021-05-07 |  | 2021-05-14
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Interim Report (24/11/2020) |  | 8 | 4 | 10 | 5 | 100%
Dissertation (29/04/2021) |  | 41 | 16 | 59 | 2 | 0%
Software System (29/04/2021) |  | 1 | 56 | 1 | 59 | 80%
Project Initialisation |  | 1 | 4 | 1 | 4 | 100%
| Design Wiki UI | 1 | 1 | 1 | 1 | 100%
| Implement REST API | 1 | 4 | 1 | 4 | 100%
| Design SCG UI | 3 | 2 | 3 | 2 | 100%
| Build temporary wiki tables | 3 | 2 | 2 | 3 | 100%
Build SCG UI |  | 5 | 14 | 5 | 22 | 100%
| Attributes panel | 5 | 2 | 5 | 3 | 100%
| Background panel | 7 | 2 | 11 | 1 | 100%
| Skills panel | 12 | 2 | 12 | 2 | 100%
| Class panel | 14 | 1 | 14 | 1 | 100%
| Foci panel | 15 | 2 | 15 | 1 | 100%
| Psychic powers panel | 15 | 3 | 15 | 2 | 100%
| Equipment panel | 17 | 2 | 26 | 1 | 100%
Implement SCG functionality |  | 19 | 14 | 27 | 20 | 0%
| Attributes panel | 19 | 1 | 27 | 6 | 100%
| Background panel | 20 | 2 | 33 | 8 | 100%
| Skills panel | 22 | 2 | 41 | 1 | 100%
| Class panel | 24 | 1 | 42 | 1 | 100%
| Foci panel | 25 | 1 | 43 | 2 | 100%
| Psychic powers panel | 26 | 2 | 51 | 2 | 100%
| Equipment panel | 27 | 1 | 52 | 2 | 100%
| Suggestion Algorithm | 28 | 2 |  |  | 0%
| Saving and exporting | 30 | 3 | 54 | 2 | 0%
Complete UI |  | 33 | 8 |  |  | 0%
| Use object avatars to represent objects in wiki | 33 | 2 |  |  | 0%
| Add filtering and sorting to wiki tables | 35 | 2 |  |  | 0%
| Make physical sheet imitation UI (minimap) | 37 | 4 | 58 | 2 | 0%
Add user accounts (stretch goal) |  | 41 | 8 |  |  | 0%
| Users can create accounts and login | 41 | 2 |  |  | 0%
| Users can save characters to the database and load them | 43 | 4 |  |  | 0%
| Users can save custom game objects in the database | 47 | 2 |  |  | 0%